## Sheet1
ATTENDANCE MONITORING SYSTEM USING RFID
Work Break down Structure
| Harshitha J | Shritha Bharadwaj | Yashaswini B V
Date | Task | Task | Task
2016-10-02 | Brief study on cloudsim simulator | Understanding the necessity to allocate the virtual machine | Study on the architecture of cloudsim
2016-10-03 | Assigning the work division | Listing the modules | Filling work division template
2016-10-04 | Understanding the goals | Literature survey-study of base paper | Learning cloudsim
2016-10-05 | Preparing for IA
2016-10-06 | 2nd Internals
2016-10-07
2016-10-08
2016-10-09 | Study on cloud technology | Literature survey-study of base paper | Learning cloudsim-features
2016-10-10 | Study on cloud technology | Literature survey-study of base paper | Learning cloudsim
2016-10-11 | Analysing the methodology to be followed | Understanding cloud terminology | Learning cloudsim
2016-10-12 | Learning cloudsim API'S | Understanding cloud terminology | Learning Java(Operators, datatypes,)
2016-10-13 | Learning cloudsim API'S | Understanding cloud terminology | Learning Java(functions)
2016-10-14 | Submission
2016-10-15 | Updating SRS/WBS | Preparing SRS/WBS | Preparing SRS/WBS
2016-10-16 | Updating SRS/WBS | Preparing SRS/WBS | Preparing SRS/WBS
2016-10-17 | Study on testing methods | Installing cloudsim simulator | Learning Java(Multi-threading, event handling)
2016-10-18 | Study on testing methods | Learning working on cloudsim | Learning Java(Multi-threading, event handling)
2016-10-19 | Study on testing methods | Learning working on cloudsim | Learning sample programs
2016-10-20 | Study on testing methods | Learning working on cloudsim | Learning sample programs
2016-10-21 | Study on testing methods | Learning working on cloudsim | Learning sample programs
2016-10-22 | Report Submission/preparing for review
2016-10-23 | Project review
2016-10-24 | Analysing the comments given by review panel
2016-10-25 | Discussion with guide
2016-10-26 | Search of new topic
2016-10-27
2016-10-28
2016-10-29
2016-10-30 |  | Deepavali
2016-10-31
2016-11-01 | Studying the available technologies | Literature Survey | Study about beacons
2016-11-02 | Study about Bluetooth devices | Literature Survey | Study about beacons
2016-11-03 | Study about Bluetooth devices | Finding the suitable technology for attendance monitoring | Literature Survey
2016-11-04 | Preparing for lab IA
2016-11-05 | Lab Internals
2016-11-06 | Study about BLE | Finding the suitable technology for attendance monitoring | Literature Survey
2016-11-07 | Literature Survey | Study on RFID technology | Study on short range sensing devices
2016-11-08 | Literature Survey | Study on RFID technology | Study on short range sensing devices
2016-11-09 | Preparing for lab IA
2016-11-10 | Lab Internals
2016-11-13 | Preparing for 3rd IA
2016-11-14
2016-11-15 |  | 3rd IA
2016-11-16
2016-11-17 |  | Working on seminar topics
2016-11-18 |  | Working on seminar topics
2016-11-19 |  | Working on seminar topics
2016-11-20 | Preparation for Lab Exam
2016-11-21
2016-11-22
2016-11-23
2016-11-24
2016-11-25
2016-11-26
2016-11-27
2016-11-28
2016-11-29 | Lab External Exam
2016-11-30
2016-12-01
2016-12-02
2016-12-03
2016-12-04
2016-12-05
2016-12-06 | Preparation for External Exam
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19 | Theory External Exam
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-01
2017-01-02
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07 | Holidays
2017-01-09
2017-01-10
2017-01-11
2017-01-12
2017-01-13
2017-01-14 | List of product requirements | List of product goals | Division of work
2017-01-15 | Study on Compatibility of hardware components | Literarture survey-base paper | Learning Bootstrap-buttons,forms
2017-01-16 | Learning specification on Raspberry Pi | Literarture survey-base paper | Learning Bootstrap-Tables
2017-01-17 | Finding the hardware components
2017-01-18 | Buying the hardware component
2017-01-19 | Learning specification of Raspberry Pi | Revising the database concepts | Learning Bootstrap-Tables
2017-01-20 | Connection of RFID reader with Raspberry pi | Revising the database concepts | Literature Survey
2017-01-21 | Connection of RFID reader with Arduino board | Revising the database concepts | Literature Survey
2017-01-22 | Learning embedded C | Learning database connectivity | Learning Bootstrap-dropdowns
2017-01-23 | Learning embedded C | Learning database connectivity | Learning Bootstrap-tab
2017-01-24 | Learning embedded C | Learning database connectivity | Learning Bootstrap-themes
2017-01-25 | Learning embedded C | Defining the entity for the database | Learning PHP-Embedding PHP inside HTML
2017-01-26 | Sample programs on Arduino-Blink | Creating a entity relationship model | Learning PHP-Basic Functions
2017-01-27 | Sample programs on Arduino-DigitalReadSerial,Fade | Learning how to connect database and a server | Learning PHP-Multidimensional array
2017-01-28 | Sample programs on Arduino-ReadNUID | Study on Basic queries | Learning PHP-Table handling and listing
2017-01-29 | Sample programs on Arduino-DumpInfo | Learn about JOIN | Learning PHP-Working with form data
2017-01-30 | Sample programs on Arduino-ChangeUID | Learn about LIKE with a serach engine | Learning PHP-Validation
2017-01-31 | Sample programs on Arduino-AccessControl | Learn about LIKE with a serach engine | Learning PHP-Registration
2017-02-01 | Discussion with guide and updation
2017-02-02 | Coding for RFID reader and Arduino connectivity | Designing database | Learning database server connectivity
2017-02-03 | Coding for RFID reader and Arduino connectivity | Designing database | Learning about SMS Gateway
2017-02-04 | Coding for RFID reader and Arduino connectivity | Designing database | Learning about SMS Gateway
2017-02-05 | Coding for RFID reader and Arduino connectivity | Designing database | Learning about SMS Gateway
2017-02-06 | Coding for RFID reader and Arduino connectivity | Designing database | Learning about Email Gateway
2017-02-07 | Coding for RFID reader and Arduino connectivity | Creation of tables | Learning about Email Gateway
2017-02-08 | Coding for RFID reader and Arduino connectivity | Joining Tables | Learning about Email Gateway
2017-02-09 | Coding for RFID reader and Arduino connectivity | Joining Tables | Learning about StyleSheets
2017-02-10 | Finding a solution for data transfer | Foreign key contraints | Learning about StyleSheets
2017-02-11 | Finding a solution for data transfer | Foreign key contraints | Learning about StyleSheets
2017-02-12 | Finding a solution for data transfer | Study on Complex key | Study on Website Templates
2017-02-13 | Understanding the spcification and features of wifi module | Study on combining attributes | Study on Website Templates
2017-02-14 | Connection of wifi module | Redesigning the database | Study on Website Templates
2017-02-15 | Connection of wifi module | Redesigning the database | Creating web pages
2017-02-16 | Coding for wifi module and Arduino connectivity | Redesigning the database | Creating web pages-admin page
2017-02-17 | Updations of SRS
2017-02-18 | Coding for wifi module and Arduino connectivity | Changes in the tables and its attribute | Creating web pages-faculty page
2017-02-19 | Coding for wifi module and Arduino connectivity | Changes in the tables and its attribute | Creating web pages-login page
2017-02-20 | Coding for wifi module and Arduino connectivity | Changes in the tables and its attribute | Creating web pages-registration page
2017-02-21 | Discussion with guide and updation
2017-02-22 | Coding for wifi module and Arduino connectivity | Writing queries | Creating web pages-admin portal
2017-02-23 | Coding for wifi module and Arduino connectivity | Writing queries | Linking the web pages
2017-02-24 | Preparing for review
2017-02-25 | Project review
2017-02-26 | Discussion with guide
2017-02-27 | Coding for wifi module and Arduino connectivity | Inserting the data into database | Students registration
2017-02-28 | Coding for wifi module and Arduino connectivity | Inserting the data into database | Students registration
2017-03-01 | Coding to dump the incoming data to database | Inserting the data into database | Students registration
2017-03-02 | Coding to dump the incoming data to database | Inserting the data into database | Faculty Registration
2017-03-03 | Coding to dump the incoming data to database | Inserting the data into database | Creation of website
2017-03-04 | Coding to dump the incoming data to database | Inserting the data into database | Creation of website
2017-03-05 | Coding to dump the incoming data to database | Writing queries for data insertion | Creation of website
2017-03-06 | Coding to dump the incoming data to database | Writing queries for data insertion | Creation of website
2017-03-07 | Coding to dump the incoming data to database | Writing queries for data retrieval | Creation of website
2017-03-08 | Coding to dump the incoming data to database | Writing queries for data retrieval | Creation of website
2017-03-09 | Final testing of the device | Writing queries for data retrieval | Preparing Paper
2017-03-10 | Testing | Powerpoint presentation | Preparing Paper
2017-03-11 | Testing | Powerpoint presentation | Preparing Paper
2017-03-12 | Testing | Powerpoint presentation | Preparing Paper
2017-03-13 | Testing | Powerpoint presentation | Preparing Paper
2017-03-14 | Testing | Powerpoint presentation | Additional changes and modification in ppt
2017-03-15 | Testing | Writing queries for data retrieval | Additional changes and modification in ppt
2017-03-16 | Testing | Writing queries for data retrieval | Additional changes and modification in ppt
2017-03-17 | Preparing for Technical Seminar
2017-03-18 | Technical Seminar Review
2017-03-19 | Preparing for IA
2017-03-20 | Internal Assessment
2017-03-21
2017-03-22
2017-03-23 | Discussion with Guide
2017-03-24 | Report Generation | Testing | Changes in Website
2017-03-25 | Report Generation | Testing | Addition of extra features
2017-03-26 | Report Generation | Testing | Addition of extra features
2017-03-27 | Report Generation | Testing | Report Generation
2017-03-28 | Report Generation | Testing | Report Generation
2017-03-29 | Report Generation | Testing | Report Generation
2017-03-30 | Testing | Report Generation | Report Generation
2017-03-31 | Testing | Report Generation | Report Generation
2017-04-01 | Testing | Report Generation | Addition of extra features
2017-04-02 | Testing | Report Generation | Addition of extra features
2017-04-03 | Testing | Report Generation | Addition of extra features
2017-04-04 | Testing | Paper presentation | Addition of extra features
2017-04-05 | ppt | Preparing Paper | Testing
2017-04-06 | ppt | Preparing Paper | Testing
2017-04-07 | ppt | Preparing Paper | Testing
2017-04-08 | Preparing Paper | Preparing Paper | Testing
2017-04-09 | Preparing Paper | Preparing Paper | Testing
2017-04-10 | Preparing Paper | Preparing Paper | Testing
2017-04-11 | Discussion with Guide
2017-04-12 | Preparing for review
2017-04-13 | Preparing for review
2017-04-14 | Preparing for review
2017-04-15 | Project review
2017-04-16
2017-04-17
2017-04-18
2017-04-19
2017-04-20
2017-04-21
2017-04-22
2017-04-23
2017-04-24
2017-04-25 | Preparing for IA
2017-04-26 | Internal Assessment
2017-04-27
2017-04-28
2017-04-29
2017-04-30
2017-05-01
2017-05-02
2017-05-03
2017-05-04
2017-05-05
2017-05-06
2017-05-07
2017-05-08

## Sheet2
2017-05-01
2017-05-02
2017-05-03
2017-05-04
2017-05-05
2017-05-06
2017-05-07
2017-05-08
2017-05-09
2017-05-10
2017-05-11
2017-05-12
2017-05-13
2017-05-14
2017-05-15
2017-05-16
2017-05-17
2017-05-18
2017-05-19
2017-05-20
2017-05-21
2017-05-22
2017-05-23
2017-05-24
2017-05-25
2017-05-26
2017-05-27
2017-05-28
2017-05-29
2017-05-30
2017-05-31